## Dated cover
Usable-material coverage by need event
Enter a dated balance in one consistent item/unit per row; retain negative closing balances to expose shortages.
Yellow cells are editable. Gray cells calculate. Replace the EXAMPLE row before using this for live work.
30 rows are prepared. To add more, copy the last table row including formulas, formats, and dropdowns.
Use one Dated cover row per item/site need event. Copy the previous event closing balance into the next event opening input after checking intervening demand and supply.
Event ID | Item / site / unit | Need date | Opening usable qty | Arrivals usable before event | Demand qty | Other allocation qty | Closing usable balance | Shortage qty | Planning owner | Plan state | Timing / balance evidence
EXAMPLE-01 | Housing / Plant A / each | 2026-10-14 12:00 | 120 | 0 | 180 | 0 | -60 | 60 | Example planner | Residual gap | Need 10:00 local; no incoming lot released before demand
Usage notes
Closing balance = opening usable quantity + arrivals usable before the event - demand - other allocations. Shortage is the magnitude of a negative balance; both results are visible.
Enter explicit zero for no arrivals or other allocations. Unknown supply stays blank and leaves the calculation blank.
This is event-level planning, not an inventory ledger. Reconcile row-to-row carry-forward manually; include receipts after one event only in the later event opening or arrivals, never both.
Do not mix units or add unapproved substitutes, blocked lots or merely dispatched material to usable supply.
Only include arrivals expected usable before that specific demand event. Confirm receiving and quality timing with the responsible owners.
Use the same Event ID in Options and milestones. Costs and recovery decisions require the authorized owners; calculated coverage is not approval.
Companion guide: https://mandel.ai/blog/supplier-delivery-delay-recovery-plan

## Options and milestones
Recovery options, approvals and checkpoints
Repeat the Event ID for each alternative or milestone. Describe the quantity and unit explicitly in the option.
Yellow cells are editable. Gray cells calculate. Replace the EXAMPLE row before using this for live work.
30 rows are prepared. To add more, copy the last table row including formulas, formats, and dropdowns.
Use one Dated cover row per item/site need event. Copy the previous event closing balance into the next event opening input after checking intervening demand and supply.
Event ID | Option / quantity / unit | Ready condition / evidence | Expected usable date | Booking cutoff / time zone | Incremental cost | Currency | Decision owner | Approval state | Next checkpoint | Milestone owner / action | Outcome / evidence
EXAMPLE-01 | Express first 200 housings, each | Supplier release by Oct 12 14:00 local | 2026-10-13 12:00 | Oct 12 14:00 America/New_York | 480 | USD | Example buyer | Pending | 2026-10-12 12:00 | Example logistics lead: confirm release before cutoff | Illustrative estimate only; receiving capacity confirmation pending
Usage notes
Costs are incremental estimates or actuals as labeled in Outcome / evidence. Keep each row currency explicit and do not total unlike currencies.
Record the fallback decision before the cutoff. A booking quote or document arrival does not prove usable material.
Close recovery only after the required usable quantity or authorized alternative disposition is evidenced. Finance owns separate cost claims or credits.
Only include arrivals expected usable before that specific demand event. Confirm receiving and quality timing with the responsible owners.
Use the same Event ID in Options and milestones. Costs and recovery decisions require the authorized owners; calculated coverage is not approval.
Companion guide: https://mandel.ai/blog/supplier-delivery-delay-recovery-plan